## Cover
Template Name | Template in details | Stage | Describe
01-XXX Project Delivery All-in-One List_V1.0 | Cover | Before implementation
| 00 Project Background | Before implementation
| 00 HLD | Before implementation
| 00BOQ | Before implementation
| 00 Server Hardware | Before implementation
| 01 SOW | Before implementation
| 01 Customer Requirements | Before implementation
| 01 Version Config guide | Before implementation
| 01 Disk Partition | Before implementation
| 01 Risk | Before implementation
| 02 Deploy infor collect | Implementation
| 02 SOP | Implementation
| 03 LLD | Implementation
| 03 IP Planning | Implementation
| 04 Onsite Problem | Implementation
| 04 Customer Requirements Change | Implementation
| 04 Password | Implementation
| 05 User Acceptance Test | Implementation
| 05 Inspection & knowledge trans | Implementation

## 00 Contact List
Role | Name | E-mail | 一期scope: 8月31号前
H3C Team |  |  | 1. 软件安装：主+备共两套控制器
PM |  |  | 2. spine+leaf+border+FW设备纳管
Lead |  |  | 3. 业务迁移：有线+无线业务，和第三方LDAP对接；出口业务仍在旧网，ADCampus与旧网对接
R&D Expert
R&D Expert
R&D Expert
Support Engineer
Support Engineer
Support Engineer
BD Director
Partner Team
PM

## 00 HLD
整体架构-混合架构
Spine和Leaf使用H3C产品
接入和WLAN使用其他公司产品
其他公司的AC与Spine连接
Border仅进行IP转发，从Vxlan架构中移除
高可用性（HA）
建议AD-Campus采用3节点的集群架构
Border（路由器-交换机）由于与SINET通过BGP建立对等关系，采用IRF2
Spine和Leaf采用M-LAG架构进行全网状连接
接入使用其他公司产品
AC使用其他公司产品
防火墙为RBM（远程备份管理）
建议使用微软DHCP服务器
认证连接
无线：其他公司的AC通过Radius协议与AD-Campus的EIA模块连接
认证点：有线服务的认证点是Leaf层；无线服务的认证点是AC
认证方式
无线做802.1X认证；
有线第一次做mac-portal认证，第二次radius认证。

## 01 SOW
SOW: Responsibility Matrix
No | Task | H3C Delivery Team |  |  | Channel Partner | Customer
|  | H3C-HQ | H3C-RO | ASP
1 | Customer information collection | S |  |  | E
(current network topology, customer requirement)
2 | HLD, Project/Scheme Design | E |  |  | S
3 | Engineering environment preparation | S |  |  | E
(power, cabinet ready)
4 | LLD Implementation | E |  |  | S
5 | Device Script/Configuration | S |  |  | E
6 | Engineering environment preparation | S |  |  | E
7 | Installation, commissioning and joint commissioning | E |  |  | S
8 | UAT of Unit test | S |  |  | E
9 | UAT of Joint test (Option)
10 | Knowledge Transfer | E |  |  | S
Remark:
E: Execute, The executive body, as the leader and responsible party to perform specific tasks, organizing meetings and discussions in the process of service delivery;
S: Support, support and cooperation, provide necessary cooperation in the service delivery process, such as solution discussion, problem confirmation, providing information and resource.

## 01 Customer Requirements
Customer Requirements
Item | Description | Confirm | IRMS编号
1 | ladp & EIA与google/O365对接 | ADCampus 7.2支持
2 | ADCampus与Teams/slack告警对接 | ADCampus 7.2支持
3 | 有线用户首次认证方式为mac-portal，第二次使用radius认证 | ADCampus 7.2支持
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## 01 Action List
H3C TS确认
No. | Action | 確認項目 | 确认项 | 確認結果 | 确认信息 | 备注
0 | 前期准备・事前準備 | 02-device introductionを参照して、デバイスリストを確認 | 设备数量确认，参考02-device introduction表格
|  | UC及びCampusのライセンスとコンポネットを確認 | UC和campus涉及的组件清单及license清单 | H3Cが用意
|  | 各E-FLOWの申請番号及び申請状況 | 需求电子流单号及具体需求（Campus） | H3Cが用意
|  | PTM E-FLOWの申請状況 | PTM电子流 | H3Cが用意
|  |  | 托付电子流是否下行至10环节 | H3Cが用意
1 | 软件安装・SWのインストール |  | 软件版本 | H3Cが用意
|  | iWM用ディスク容量の用意 | 是否需要提前预留iWM组件安装位置 |  | 除了UC以及Campus的组件之外，还需要预留无线纳管的iWM和iWO的安装资源
|  | iWO用ディスク容量の用意 | 是否需要提前预留iWO组件安装位置
|  | UCのホスト名（3台） | 服务器主机名：sdnhost01, sdnhost02, sdnhost03 root密码：Pwd@314159 |  |  | 命名：仅支持小写字母、数字、连字符和小数点，不能以0开头且全为数字，不能以0x、连字符、小数点开头，不能以连字符、小数点结尾 密码：可以先配置初始密码，项目交付完成后客户可自行修改
|  |  | 磁盘分区 | H3Cが用意
|  |  | IP规划 |  |  | 需要客户提供可用IP地址段，建议提供/16及以上网段，供整个项目使用（不包含业务网段）
2 | LDAP对接・認証サーバとの連携 | LDAPサーバの設置場所やIPアドレス | 位置，IP （如何互通） |  | 一期不对接现网认证业务，只做路由可达（考虑手配路由） | 推荐LDAP通过L3交换机与ADCampus互通
|  | LDAP Server Name | LDAP Server Name
|  | admin DN, admin password | admin DN, admin password
|  | base DN | base DN
|  | sub-base DN | sub-base DN 每网段每sub-base DN？ |  |  | 绑定user-group
|  | CA認証局を確認、証明書認証使用しているかどうか | CA服务器是否存在，怎么对接现网证书服务器
3 | 设备上线・ZTP | スイッチのホスト名 | 命名 |  |  | 02-Naming Plan 建议设备命名根据设备位置规划，如楼号_楼层_机柜_机架
IP规划
|  | 業務用VLANやサブネットの一覧表（有線、無線） | 现网vlan规划，包括有线业务vlan，无线业务&管理vlan |  | 需要计算各个网段所需主机数同步给客户，结合后续二期与三期的部署酌情增加
|  |  | VLAN规划 |  |  | 需要客户提供可用vlan范围
|  | スイッチのログインアカウントやパスワード | 设备登录用户名密码 admin/Pwd@314159 |  |  | 可以先配置初始密码，项目交付完成后客户可自行修改
|  | シリアル番号一覧 | 设备SN | H3Cが用意 | 设备还未发货，等待装箱单
|  | 各フロアのアクセスSW台数 | 每栋楼leaf、access设备的数量需要确认 |  | 代理商正在确认
|  | 検証用のユーザーの用意（LDAP上） | 测试网段、用户 |  | 可以协调测试环境与测试用户 | ADCampus环境搭建完成后，用于正式割接前的业务测试
4 | 有线业务部署・有線業務展開 | 端末の種類（ダム端末の有無、固定IP端末）、ネットワーク方式、認証方式 | 终端类型（是否有哑终端，静态IP终端），组网方式，认证方式 公共机建议802.1X认证 静态IP终端--静态IP用户认证 |  | 一期不涉及，二期以及三期涉及到哑终端以及部分静态IP的终端。 认证方式第一次SSO认证 获取证书，后续直接证书认证。 静态IP终端可以固定终端IP 不需要IP随用户变更。 公共机IP也固定，不需要随用户变更。
|  | 実MACを学習する必要がある端末の有無 | 是否有特殊终端，如需要开启代答的场景 |  | 真实MAC学习终端情况不明，需要澄清后续变更的影响范围。
|  | マルチキャスト業務の有無 | 是否有组播业务 |  | 不确定是否涉及组播业务，考虑到其他局点 建议开启组播业务
|  | radius又はLDAP server IP | radius server IP
|  | 有線や無線端末のIP収得方式（D & S） vDHCP or MSDHCP | 终端获取地址方式： 静态IP or 动态IP vDHCP or 微软DHCP (微软DHCP涉及配置调整) 微软DHCP利旧还是新建，松耦合还是紧耦合对接 微软DHCP是不是同时对接有线用户和无线用户 |  | 使用vDHCP； 一期我司不涉及认证，只负责免认证下发地址，二期三期正常流程。
|  | 業務用VLANやサブネットの一覧表 | 有线业务网段&vlan&命名信息 |  | 业务网段已经收集，涉及VLAN1~100；4093 以及4094； 需要考虑access下行不做配置变更接入Campus | 二层网络域，安全组，接入策略，LDAP同步策略都使用相同命名
|  | 異なる業務サブネット間通信の有無 | 有无东西向流量需要放通（VPN命名）
|  | 他社Access SWの設定変更（UPlink trunk all） | spine-leaf--第三方access配置注意事项 *第三方access控制器不纳管 |  | 第三方接入需要做的配置更改需要澄清，客户侧希望尽量减少对下行口的影响。
|  | 外部からのリモートアクセス（VPN設定） | 外网访问内网--控制器纳管M9K需要EAD安全检查；FW与其他网络设备打通VPN，远程接入认证。 | H3C内部確認中 | 未定，需要结合M9K业务部署情况而定（有远程访问需求 结合EAD做安全检查 已经购买SSLVPNLicense）
|  | 既存Access SWのアップリンクポート個数（LeafはM-lag構成の為） | 现在access-leaf的接口有几个 adcampus网络中，access需要两个接口双上行连到leaf |  | 现网边缘大部分是堆叠，所以接入大部分应该有上行2端口，针对端口不足的设备 考虑修改LACP的最小成员数UP，不考虑冗余。
5 | 无线业务部署・無線業務展開 |  | spine-leaf-第三方access spine-leaf-我司access
|  | 現在無線LANの管理や業務サブネットのGW | 当前无线业务网关、管理网关的部署方式 建议无线业务网关配置在AC，spine、leaf放通对应vlan即可 |  | 一期不涉及，后续使用我司无线后 大概率本地转发，认证点在AC，用户认证设计第一次SSO认证，后续证书认证；需要对接Google与MS365；
|  | 無線の認証ポイント：AC or EIA | 无线认证点：AC or EIA
|  | 無線端末の認証方式・Google/office365との接続の有無 | 无线用户认证方式，是否需要对接Google/office365
6 | 业务割接・切替作業 | 切替はサブネット単位で行えるかどうか | 割接方式：是否支持按网段割接 网段和地理位置的关系 |  | 一周内割接完所有业务；割接前可以有3天割接测试时间；
|  |  | 确认：网段数量，有线用户数量，无线用户数量，VPN规划 |  | 东西向流量需要互访，考虑一期只做设备纳管（剩余配置手动配置） 有线无线业务需要互访，有线无线为同一账号 同一认证服务器；
割接过程中，东西向流量互访需要调整FW策略
|  | ユーザ情報は有線と一緒でしょうか | 有线、无线业务是否需要互访
有线、无线用户是不是同一个认证账号，认证服务器？
一期：有线mac portal，无线做portal认证，不对接office 365 二期：升级到7.2，需要确认无线是否需要对接office 365
7 | 逃生配置・緊急用DHCP | サブCampusの構築完了までは冗長されない | 逃生DHCP server具体信息 |  | 一期不涉及灾备，后续下单另一套Campus与仲裁服务器。
推荐配置逃生优化方案
8 | 出外网配置・インターネットへの通信 | 推奨構成：spine--border--Sinet | 互联推荐：spine--border--外网设备 |  | 不考虑更换FW部署方式，FW配置翻译由我司FW研发与一线承担。
|  | NATは必須になるでしょうか | 外网设备有几台，能提供几个接口？ |  | 一期出口为100G单出口，上行接外网还在进行规划。出外网配置手配
一期： spine出外网配置建议手配，方案更加灵活 参考现存GW与core的配置
二期： 路由配置，参考现存GW与ISP对接的方式和配置
9 | 防火墙配置 |  | 建议FW旁挂在spine | H3C内部確認中
|  |  | 现网安全策略整理 | H3C内部確認中
|  |  | 推荐方案：FW与spine、border互联配置、路由手配，SMP只负责下发安全策略 | H3C内部確認中
10 | license信息 |  |  | H3C内部確認中
11 | 业务测试 |  |  | H3C内部確認中

## 01 Software Version
Products | ADCampus 7.1 | ADCampus 7.2
OS | NingOS_V3.1.0
Unified Platform | BMP E7104, UDTP E7104
NSM | E0714
SeerEngine-Campus | E0714
vDHCP Server | R7102
SeerAnalyzer | E0715
EIA-V9 | E7102
Cloudnet | E0714
EAD | E7102
iNode | /
License Server | E1212
LS-6530X-24X8C | /
LS-6520X-54HC-UPWR-EI | /
LS-6550X-56HF-HI | /
NS-SecPath M9000-X06 | /
LS-10506X-G | /

## 01 Disk Partition
Mount Point | Minimum Capacity | Applicable Mode | File Type | Remarks
System disk |  |  |  |  | raid1
/var/lib/docker |  | BIOS mode/UEFI mode | XFS | Capacity expandable
/boot |  | BIOS mode/UEFI mode | XFS | N/A
Swap |  | BIOS mode/UEFI mode | Swap | N/A
/var/lib/ssdata |  | BIOS mode/UEFI mode | XFS | Capacity expandable
/ |  | BIOS mode/UEFI mode | XFS | Capacity expandable
/boot/efi |  | UEFI mode | N/A | N/A
Reserved disk |  | N/A | N/A | Used for GlusterFS
Total | 4405G/6.5T
/var/lib/etcd |  | BIOS mode/UEFI mode | XFS | separate physical disk
Total | 500/600G
Data Disk
/sa_data |  |  | N/A | N/A
/sa_data/mpp_data |  |  | ext4 | N/A
/sa_data/kafka_data |  |  | N/A | N/A
Total | 2000/2.4T

## 01 Risk
No. | Risk Description | Status | Progress | Next Step | Owner
1
2
3

## 02 Deploy infor collect (hidden)
项目 | Item | 描述 | Description
现网信息，互访需求 | Current network status/details/information，Access requirement/interaction requeirement | 可在拓扑图中呈现（与前期工期是否有关联，是完全独立吗）有无互访需求 | Please present in Network topology if possible (related to the phase 1 and phase 2 or completely separate? ) in Network topology，campus if possible (related to the others or completely separate? )
提供网络拓扑图（客户提供) | Network topology | 1. 服务器和L3交换机之间的网口如何连接？ 2. leaf和access之间的组网？ 3. spine和外网的连接方式？ 4.leaf、access是否要堆叠 5.Leaf下行连接到AP的接口是聚合口还是单端口？总共有多少个这样的接口？ （明确campus环境中的组网方式） | 1. How are the network ports between the server and the L3 switch connected? Does it involve link aggregation, and does the UC, controller, and analyzer use separate NICs or a common NIC? 2. the network connection between leaf and access? 3. how the leaf and firewall connected ? 4. Does access have stacking and cascading? 5. Is the downstream interface of access to the AP an aggregated port or a single port? How many such interfaces are there in total? (Clarify the networking method in the campus environment)
可用网段/vlan | Avaiable network segment/vlan | 避免campus和其他冲突 | To avert conflict between Campus and others current network segment
业务网段有哪些 | Network segment for business | 请详细列出 | Please list them in details if possible
安全组有哪些 | How many security groups? And what are they? | 规划原则：相同权限用户属于一个安全组 安全组之间是否需要进行互访 | Accounts under the same authority shall be put into the one security group. security group if possible related to the others or completely separate?
是否需要划分私网，实现各安全组强隔离、强制不互访需求， | Private Network needed? Strong isolation or no access between security groups | 若有，计划规划多少个私网（如财务、监控、校园一卡通等业务） | If yes, how many private networks planned? (eg. Finance, mornitoring system, campus etc.)
名称定义：创建的私网/安全组/二层网络域/设备等、接入用户/接入策略/接入组等、无线SSID命名； | Name definition: Private network created/security groups/L2 network domain/device, etc. access users/access strategy/access group, etc. wireless ssid name
现有的认证方式 | Current Authentication mode? | 主要有线和无线终端类型，现有终端是否有特殊要求，比如固定IP、公共机 | Including wired and wireless terminals, any special requirement for the current terminals (eg. Fix IP or public computer); whether fixed ip address for terminasl or one pc shared by more than one person?
认证方式 | Authentication Mode | mac、802.1x、mac portal | mac、802.1x、mac portal
有线用户如何接入网络，涉及认证吗（看清单没有EIA）,如果有，反馈下有线终端最大接入数量 | How do wired users access the network, and how many？ |  | does it involve authentication (see the list without EIA), if so, feedback on the maximum number of wired terminals to access
是否存在同一账户多个接入场景 | One account will access/interact into more than one scenarios？ | 即在不同场景获取不同地址 | Different addresses acquired in different scenarios.
是否有哑终端 | Any dumb terminals in the campus network? | 哑终端的类型和连接方式是什么，哑终端能否主动发包（如打印机，摄像头，刷卡机等） 哑终端认证信息收集：如mac地址； | 1.What are the types and connection modes of the dumb terminals? Are such terminals able to send package proactively? (eg. Printer, camero, ) 2.Authentification information for dump devices, like MAC
其他特殊情况补充，如特殊终端或特权账号等 | Other special conditions, like special terminals or special authority accounts
AD Campus方案认证帐号创建方式 | The creation method of the verified accounts for AD Campus solution | LDAP、手工导入、第三方认证 | LDAP, manual import or third-party authentication
是否涉及准出认证（三方AAA服务器） | Any third party charging AAA server? | 如果涉及，准出认证设备及服务器分别是什么厂商的什么设备，计划如何对接，是否涉及对接开发 | If it is involved, what are the certified equipment and server, how we plan to connect, and whether it involves the development of the connection?
DHCP 逃生server（必选项，除非明确不需要逃生） | DHCP escape server (required option, unless it is clearly not needed to escape) | 使用windows DHCP server单机部署（主推模型）还是自购的第三方DHCP server，具体型号是什么 | Use windows DHCP server stand-alone deployment (main push model) or self-purchased third-party DHCP server, what is the specific model If not，plz risk warning
IP地址规划 | 作用 | 备注
Master节点1 IPv4 | 为安装了H3Linux操作系统的Master节点分配的IPv4地址 | 部署IPv4必选项（单机部署模式只需要一个Master节点）
Master节点2 IPv4 | 为安装了H3Linux操作系统的Master节点分配的IPv4地址
Master节点3 IPv4 | 为安装了H3Linux操作系统的Master节点分配的IPv4地址
Master节点1 IPv6 | 为安装了H3Linux操作系统的Master节点分配的IPv6地址 | 部署IPv6必选项（单机部署模式只需要一个Master节点）
Master节点2 IPv6 |  | 加入同一集群的所有Master节点的IPv6地址必须处于同一网段
Master节点3 IPv6 | 为安装了H3Linux操作系统的Master节点分配的IPv6地址
北向业务虚IP(IPv4) | 为安装了H3Linux操作系统的Master节点分配的IPv6地址
| 用于提供集群的北向业务，可使用该地址登录集群的Web页面 | IPv4环境部署时必选项
北向业务虚IP(IPv6) |  | 北向业务虚IP必须在Master节点所处的IPv4网段内
| 双栈环境下生效，用于提供集群的北向业务，可使用该地址登录集群的Web页面 | IPv6环境部署时必选项
集群内部虚IP |  | 北向业务虚IP必须在Master节点所处的IPv6网段内
| 用于集群内部通信的IP地址 | 必选项
Worker节点IP |  | 集群内部虚IP必须在Master节点所处的网段内
| 安装H3Linux操作系统 | 可选项
SeerEngine-Campus节点IP |  | Worker节点的IP地址必须与加入同一集群内的Master节点的IP处于同一网段
SeerEngine-Campus集群IP | 控制组件的节点地址 | SeerEngine-Campus集群包含的三个节点地址，具体网络规划可参考6.2 组网&IP规划
vDHCP集群IP | 控制组件的集群地址，用于提供TFTP服务 | SeerEngine-Campus的集群地址
vDHCP | vDHCP的集群地址 | vDHCP的集群地址，实际不使用
EIA | DHCP服务器的节点地址 | vDHCP服务器使用的两个节点IPv4地址, 具体网络规划可参考6.2 组网&IP规划
EIA IPv6 | EIA服务器的IPv4地址 | 复用集群北向业务虚地址 (IPv4)
| EIA服务器的IPv6地址 | 复用集群北向业务虚地址 (IPv6)
表4-5 用户业务资源规划
规划项 | 数据示例 | 说明
教师安全组网段（网关） | 20.0.0.0/16(20.0.0.1) | 教师安全组用户使用的网络
BYOD安全组网段（网关） | 50.0.0.0/16(50.0.0.1) | BYOD用户使用的网络
Guest网段（网关） | 22.2.2.0/24(22.2.2.1) | Guest用户使用的网络
认证失败网段（网关） | 33.3.3.0/24(33.3.3.1) | 认证失败用户使用的网络
逃生网段（网关） | 40.0.0.0/16(40.0.0.1) | 逃生用户使用的网络
for example
Item | Data examples | Confirm
Server IP |  | For OS master IP
集群内部虚IP
北向内部虚IP
SeerEngine-Campus集群IP | 110.1.0.100 | SeerEngine-Campus的集群地址
SeerEngine-Campus节点IP | Node1：110.1.0.101 | SeerEngine-Campus集群包含的三个节点地址
Node2：110.1.0.102
Node3：110.1.0.103
vDHCP集群IP | 110.1.0.104 | vDHCP服务器的集群地址,实际不使用
vDHCP节点IP | Node1：110.1.0.105 | vDHCP服务器使用的两个节点地址
Node2：110.1.0.106
微软DHCP的IP | 8.0.1.171 | 微软DHCP服务器使用地址
EIA | 100.1.0.100 | EIA服务器的地址
VLAN 1 网段（网关） | 120.1.0.0/24(120.1.0.1) | VLAN 1的网络，用于自动化上线
VLAN 4094网段（网关） | 130.1.0.0/24(130.1.0.1) | VLAN 4094的网络，用于控制组件和设备通信
VLAN30网段（网关） | 100.1.0.0/24(100.1.0.1) | 统一数字底盘&SeerEngine-Campus&vDHCP使用的网段
VLAN 91 网段 | 91.1.0.0/24 | 手工纳管时Spine与Leaf通信使用的VLAN，underlay网络，建ospf邻居
Underlay IP网段（loopback地址） | 200.1.1.0/24 | Spine与Leaf环回口地址网段，EVPN网络，建立BGP邻居
VLAN 4093网段（无线AC4093地址） | 130.3.0.0/24 | VLAN4093三层接口作为与AP通信接口
Item | Describe | Detail
Server IP | Same segment | For OS master IP
集群内部虚IP
北向内部虚IP
SeerEngine-Campus集群IP | 南向网络，可以和北向相同或者不同网段 | SeerEngine-Campus的集群地址
SeerEngine-Campus节点IP |  | SeerEngine-Campus集群包含的三个节点地址
vDHCP集群IP | 三台集群则两台进行HA | vDHCP服务器的集群地址,实际不使用
vDHCP节点IP |  | vDHCP服务器使用的两个节点地址
微软DHCP的IP | 逃生dhcp | 微软DHCP服务器使用地址
EIA | 复用北向地址 | EIA服务器的地址
VLAN 1 网段（网关） |  | VLAN 1的网络，用于自动化上线
VLAN 4094网段（网关） |  | VLAN 4094的网络，用于控制组件和设备通信
VLAN30网段（网关） |  | 统一数字底盘&SeerEngine-Campus&vDHCP使用的网段
VLAN 91 网段 |  | 手工纳管时Spine与Leaf通信使用的VLAN，underlay网络，建ospf邻居
Underlay IP网段（loopback地址） |  | Spine与Leaf环回口地址网段，EVPN网络，建立BGP邻居
VLAN 4093网段（无线AC4093地址） |  | VLAN4093三层接口作为与AP通信接口

## 02 SOP (hidden)
ADCampus Project Woriking Flow
Delivery process |  |  |  | Expecting duration | Output | Status | Open date | Closed date | Risk | Next step &ower
0. Collect requirements from customer |  |  |  | NA
1. Before implementation | 1.1 kick-off meeting | team members |  | 1 day | AM_Pixel ADCampus delivery information table
network topology customer requirements
remote access
| 1.2 Information | hardware resource: CPU, storage, memory
software version
| 1.3 network scheme | IP planning | controller, analyzer
underlay，overlay
business network
device SN, MAC
underlay login
| 1.4 Physical connection |  |  | 1 day
1.5 Device upgrade
1.6 AD-NET software download
2. Software installation | 2.1 matrix, UC, cluster |  |  | 3 days | ADCampus Solution Implementation Scheme Template
2.2 controller, analyzer, EIA, WSM, Vdhcp
2.3 license server
2.4 license registration
2.5 escape DHCP
3. Device online | 3.1 spine/leaf/access online |  |  | 1-2 days / fabric
3.2 AC AP online
4. Service deployment | 4.1 controller | wired authentication |  | 3 days
wireless authentication
Internet
| 4.2 Analyzer |  |  | 2 days
5. Service test | 6.1 SDN HA test | controller HA |  | 2 days | ADCampus Solution Emergency Drill Test Report
analyzer HA
license server HA
data backup and restore
| 6.2 Network HA test | Spine HA
Leaf HA
Aggregation HA
AC HA
DHCP HA
6. Project quality inspection |  |  |  | 1 day | ADCampus Solution Project Quality Inspection Report Template
7. hand over |  |  |  | 1 day | AM_Pixel ADCampus delivery information table ADCampus Solution Emergency Response and Recovery Guide
8. service completion report |  |  |  |  | Service completion Email

## 02-Device Introduction
S6550X-HI Switch | 教育棟*2 + SH棟*2
H3C SecPath M9000-X06 | 教育棟*1 + SH棟*1
H3C S10506X-G | 教育棟*1 + SH棟*1
H3C S6530X-48Y8C |  | 位置 | H3C S6530X-48Y8C | LS-6520X-54XC-UPWR-SI
|  | Dist SW & Server Room SW (教育棟) | 2 | 2
|  | Dist SW & Server Room SW(SH棟) | 2 | 2
|  | Dist SW & 3F EPS Floor SW(大学1号館) | 2 | 1
|  | Dist SW & 3F EPS Floor SW(大学研究室棟) | 2 | 1
|  | Dist SW & 1F EPS Floor SW (UCH) | 2 | 1
|  | Dist SW & 2F EPS FloorSW (ELF) | 2 | 1
|  | Dist SW & 1F EPS Floor SW (CH棟) | 2 | 1
|  | Dist SW & 3F EPS Floor SW (大学6号館) | 2 | 2
|  | Dist SW(新町田変電所付近集約スイッチ(新設) | 2 | 0
|  | Floor SW (実技実験棟(更改)) | 0 | 1
|  | Dist SW & 1F EPS Floor SW (K12経塚) | 2 | 1
|  | Dist SW & 1F EPS Floor SW (経塚オフィス棟) | 2 | 2
|  | Dist SW & 2F EPS Floor SW (K12中央) | 2 | 2
|  | Dist SW & 3F Floor SW(本部棟) | 2 | 3
|  | Dist SW & 3F Room SW(本部棟) | 0 | 1
|  | Dist SW & 2F Floor SW(研究棟センター) | 2 | 1
|  | Dist SW & 1F Floor SW(K12東山(中央)) | 2 | 2
|  | Dist SW & 2F Floor SW (K12東山(学習棟)) | 1 | 3
|  | Dist SW & 3F Floor SW(SeiTechCenter) | 2 | 3
|  | 总计 | 33 | 30
|  |  | 34 | 30
H3C S6520X-54XC-UPWR-SI
MSR1008

## 02-Network Connection Design
P-peerlink, K-keepalive, D-downlink, U-uplink, C-connect, R-reserved, M-mgmt
设备 | 数量 | 光模块 | 教育棟 | SH棟 |  | 6550X-56HF-HI (48*SFP28 Ports,8*QSFP28 Ports)
S6550X-HI Switch | 2+2 | QSFP-100G-SR4-MM850 | 6 | 4 | 短距离 | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51 | 53 | 55
|  | QSFP-100G-LR4L-WDM1300 | 4 | 4 | 长距离 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56
|  | QSFP-100G-D-CAB-1M | 2 | 2 | 直连
|  | SFP-25G-LR-SM1310 | 4 | 4
|  | SFP-XG-SX-MM850-A |  | 2
H3C SecPath M9000-X06 | 1+1 | SFP-XG-LX-SM1310 | 8 | 8 |  | 6550X-56HF-HI (48*SFP28 Ports,8*QSFP28 Ports) 1 2: SecPath M9000-X06 (48*SFP+ Ports, 6*2*100G Ports)
[6 empty] | 1 |  |  |  | 3 |  |  |  | 5 |  |  |  | 1 |  |  |  | 3 |  |  |  | 5
[6 empty] | 2 |  |  |  | 4 |  |  |  | 6 |  |  |  | 2 |  |  |  | 4 |  |  |  | 6
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24
H3C S10506X-G | 1+1 | SFP-XG-LX-SM1310 | 21 |  |  | 2 1 2: 10506X-G (48*SFP+ ports, 4*QSFP28 Ports, 36*2*QSFP28 Ports)
|  | QSFP-100G-LR4L-WDM1300 | 18 |  | 长距离 | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | QSFP-100G-SR4-MM850 | 12 |  | 短距离 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | SFP-XG-SX-MM850-A | 20
|  | SFP-25G-LR-SM1310 | 4 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35
|  | SFP-25G-SR-MM850 | 4 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36
MSR1008 | 5 |  |  |  |  | 1 2 1 2: MSR1008 (2*10GE(SFP+),2*GE(Combo),8*GE)
[6 empty] | 2 | 4 | 6 | 8 |  |  |  |  | 0
[6 empty] | 3 | 5 | 7 | 9 | 10 | 11 | 0 | 1 | 1
Dist SW & Server Room SW | [5 empty] | 1 2 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2+2 | SFP-GE-SX-MM850-A |  | 10 |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 2+2 | QSFP-40G-D-AOC-7M | 4 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-XG-SX-MM850-E | 38 | 32
|  | QSFP-100G-LR4L-WDM1300 | 4 | 4
|  | QSFP-100G-SR4-MM850 | 4 | 4 |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | QSFP-100G-D-CAB-1M | 2 | 2 | 直连 | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | LSWM2STK | 1 | 1 |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | QSFP-40G-SR4-MM850 | 8 | 8
|  | SFP-25G-SR-MM850 | 8 | 8 |  | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 1; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 3 4: 3; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 5 6: 5; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 7 8: 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F EPS Floor SW(大学1号館) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-GE-SX-MM850-A | 4 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-GE-LX-SM1310-A | 3
|  | SFP-10GE-T | 16
|  | QSFP-100G-D-CAB-1M | 2 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | QSFP-40G-SR4-MM850 | 4 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | LSWM2STK | 1 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F EPS Floor SW(大学研究室棟) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-10GE-T | 11 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | LSWM2STK | 1
|  | QSFP-40G-SR4-MM850 | 4 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 1F EPS Floor SW (UCH) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | SFP-10GE-T | 4 +6 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | QSFP-100G-D-CAB-1M | 2 +2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-40G-LR4L-WDM1300 | 8 + 8
|  | QSFP-40G-D-AOC-7M | 2
|  | SFP-GE-SX-MM850-A | 4 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | SFP-GE-LX-SM1310-A | 6 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | QSFP-40G-SR4-MM850 | 4 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | LSWM2STK | 1
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 2F EPS FloorSW (ELF) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-10GE-T | 24 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | QSFP-40G-SR4-MM850 | 4
|  | LSWM2STK | 1 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 1F EPS Floor SW (CH棟) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-10GE-T | 4 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-XG-SX-MM850-E | 8
|  | QSFP-100G-D-CAB-1M | 2
|  | QSFP-40G-SR4-MM850 | 4 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | LSWM2STK | 1 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F EPS Floor SW (大学6号館) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | SFP-GE-SX-MM850-A | 20 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | SFP-GE-LX-SM1310-A | 2
|  | QSFP-40G-SR4-MM850 | 8 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | LSWM2STK | 1 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW(新町田変電所付近集約スイッチ(新設) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 10 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI |  | QSFP-100G-D-CAB-1M | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | LSWM2STK | 1
6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Floor SW (実技実験棟(更改)) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C |  | SFP-GE-LX-SM1310-A | 2 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | QSFP-40G-LR4L-WDM1300 | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-10GE-T | 2
6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 1F EPS Floor SW (K12経塚) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-GE-SX-MM850-A | 30 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | QSFP-40G-SR4-MM850 | 4
|  | LSWM2STK | 1 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | SFP-10GE-T | 5 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 1F EPS Floor SW (経塚オフィス棟) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 2 | SFP-GE-SX-MM850-A | 1 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-GE-T-D | 2
|  | SFP-XG-SX-MM850-A | 2
|  | SFP-10GE-T | 7 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | QSFP-100G-D-CAB-1M | 2 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | QSFP-40G-SR4-MM850 | 8 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | LSWM2STK | 1
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 2F EPS Floor SW (K12中央) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 2 | SFP-GE-SX-MM850-A | 36 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-10GE-T | 2
|  | SFP-XG-D-AOC-7M-H | 2
|  | QSFP-100G-D-CAB-1M | 2 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | QSFP-40G-SR4-MM850 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | LSWM2STK | 1 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F Floor SW(本部棟) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | SFP-GE-LX-SM1310-A | 4 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 3 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-40G-SR4-MM850 | 12
|  | SFP-10GE-T | 8
|  | SFP-XG-LX-SM1310 | 2 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | QSFP-100G-D-CAB-1M | 2 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | LSWM2STK | 1 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | SFP-XG-SX-MM850-A | 18
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F Room SW(本部棟) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | [5 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 1 | SFP-XG-SX-MM850-A | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
Dist SW & 2F Floor SW(研究棟センター)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8
LS-6520X-54XC-UPWR-SI | 1 | SFP-GE-LX-SM1310-A | 8 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | SFP-GE-SX-MM850-A | 10 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
|  | QSFP-100G-D-CAB-1M | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
|  | QSFP-40G-SR4-MM850 | 4
|  | LSWM2STK | 1 |  |  | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 1; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 3 4: 3; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 5 6: 5; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 7 8: 7
|  | SFP-10GE-T | 1 |  |  | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 2; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 3 4: 4; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 5 6: 6; 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 7 8: 8
Dist SW & 1F Floor SW(K12東山(中央)) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 2 | SFP-XG-SX-MM850-A | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | QSFP-40G-SR4-MM850 | 8
|  | LSWM2STK | 1 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 2F Floor SW (K12東山(学習棟)) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 1 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 3 | QSFP-100G-D-CAB-1M | 2 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | SFP-10GE-T | 5
|  | SFP-GE-T | 2
|  | QSFP-40G-SR4-MM850 | 12 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
|  | LSWM2STK | 1 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8
Dist SW & 3F Floor SW(SeiTechCenter) | [5 empty] | 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus ) 1 2: 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports)
H3C S6530X-48Y8C | 2 | QSFP-40G-LR4L-WDM1300 | 8 |  |  | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 49 | 51 | 53 | 55 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47
LS-6520X-54XC-UPWR-SI | 3 | SFP-GE-SX-MM850-A | 40 |  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 50 | 52 | 54 | 56 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
|  | QSFP-100G-D-CAB-1M | 2
|  | QSFP-40G-SR4-MM850 | 12
|  | LSWM2STK | 1 |  |  | 6530X-48Y8C (48*SFP28 Ports,8*QSFP28 Ports) 1 2: 6520X-54XC-UPWR-SI (48*1G/2.5G/5G/10GBase-T UPoE Ports,4*QSFP Plus Ports, 8-Port 10G SFP Plus )
[6 empty] | 1 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 47 | 49 | 51
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52
[6 empty] | 1 | 3 | 5 | 7
[6 empty] | 2 | 4 | 6 | 8

## 02-Port Matrix
No | Local Device | Local Port | Port Type | Local Cabinet | Peer Cabinet | Peer Device | Peer Port | Port Type | Cable Length | Notes
MGMT-Leaf&SDN connection
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Spine-Spine connection(peer-link + keepalive)
1 | [9 empty] | M-LAG IPL
2 | [9 empty] | M-LAG IPL
3 | [9 empty] | M-LAG Keepalive
Leaf-Leaf connection(peer-link + keepalive)
1 | [9 empty] | M-LAG IPL
2 | [9 empty] | M-LAG IPL
3 | [9 empty] | M-LAG Keepalive
Border-Border connection
1
2
3
Spine-Leaf connection
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Leaf-Access connection
1
2
3
4
5
6
Leaf-Access connection
1
2
3
4
5
6
Leaf-Access connection
1
2
3
4
5
6
Leaf-Access connection
1
2
3
4
5
6
………………..
Spine-FW connection
1
2
3
4
5
6
Spine-AC connection
1
2
3
4
5
6
Spine-Border connection
1
2
3
4
5
6
Border-现存GW connection (临时)
1
2
3
4
5
6
Border-SIENT connection (二期)
1
2
3
4
5
6

## 02-Naming Plan
Product Code | Product Description | Product Serial Number | Location | Function | FLOOR-RACK No.-STOCK No. | Device Name | MGMT IP (vlan 4094) | Floor
0235A2RB
0235A2RB
0235A2RB
0235A2H3
0235A2H3
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A2WB
0235A4GD
0235A4GD
0235A2WB
0235A4GD |  |  |  |  | -

## 03 Vlan Planning
Vlan type | Vlan range | Description
默认预留 （spine-leaf-access） | 2-99
device auto online VLAN | 1 | vlan used to estalblish websocket conncetion when come online
VLAN4093 | 4093 (不可修改) | wireless mgmt IP
VLAN4094 | 4094 (不可修改) | device mgmt VLAN
VLAN2 | 2 (不可修改) | M-LAG escape VLAN
IRF MAD VLAN | 100 (不可修改) | IRF MAD VLAN
服务器与L3 Switch互联 | vlan*1 | controller -- L3SW interconnect VLAN
spine与L3 Switch互联 | vlan*2 | spine-- L3SW interconnect VLAN
border与外网交换机互联 | vlan*2 | border--external router interconnect VLAN
border与FW互联 | vlan*2
FW与spine互联 | vlan*2
园区免认证vlan池 |  | 为隔离域下的免认证分配vlan ID
园区access vlan池 有线业务vlan池 | 101-3000 | access设备上线后为其下发vlan配置 为vlan网络类型的隔离域下的有线用户分配vlan ID
无线业务vlan池 | 3501-3600 | 为vlan网络类型的隔离域下的无线用户分配vlan ID
安全组vlan池 | 3501-4000 | 为隔离域下的安全组分配vlan ID，实现用户的接入

## 03 IP Planning
Controller installation ( /24 )
IP Planning（Cluster Depolyment）
Subnet | Host Name | IP address(ipv4) | IP address(ipv6) | Description | Remarks
VLAN xx
subnet1 | Controller-01 |  |  | Controller master node 01 | recommend use separate NIC for subnet 1 and subnet 2
| Controller-02 |  |  | Controller master node 02
| Controller-03 |  |  | Controller master node 03
| Northbound virtual IP |  |  | northbound virtual IP
| License Server |  |  | License Server virtual IP
| Controller-01 |  |  | Controller node 01 container ip
| Controller-02 |  |  | Controller node 02 container ip
| Controller-03 |  |  | Controller node 03 container ip
Cluster management IP
| vDHCP node 1 |  |  | vDHCP node 1
| vDHCP node 2 |  |  | vDHCP node 2
| vDHCP cluster IP |  |  | vDHCP cluster IP
| Gateway IP |  |  | configured on MGMT switch
*分析器安装选择南向无网络
Underlay deployment
Subnet |  | IP address(ipv4) | IP address(ipv6) | Description | Remarks
BGP AS： OSPF xx area xx
VLAN 1 address pool |  |  |  | auto online IP pool | 1台设备占用一个地址，需要考虑网络扩容的场景 1组IRF设备仅占用1个地址
VLAN 4094 address pool |  |  |  | device mgmt IP | 1台设备占用一个地址，需要考虑网络扩容的场景 1组IRF设备仅占用1个地址
VLAN 4093 address pool |  |  |  | 无线管路，AP mgmt ip | 取决于AP的数量
loopback 0 IP address pool |  |  |  | BGP邻居建立，router-id 设备模板-underlay ip范围 | 每台spine+leaf设备占用一个地址
loopback 2 IP address pool |  |  |  | virtual VTEP IP | only leaf devices need this, 1 address required sharing the same ip range with M-LAG escape IP pool
M-LAG IP address pool |  |  |  | M-LAG underlay escape IP | 1对M-LAG设备需要两个地址，和loopback2共用一个IP
M-LAG keepalive IP address pool |  | 192.168.0.0/30 |  | M-LAG Keepalive (default value, do not support modification) | used by leaf device. Used internally between 2 leafs
管理网出口地址池 |  |  |  | spine与L3 Switch互联地址 | 需要2个/29位地址
出外网地址池 |  |  |  | border--外网交换机 | ECMP recommended , each vlan needs 29 mask-length ip range
Spine-FW,FW-Border
Users external escape IP address pool |  |  |  | for User external escape | in case one leaf device's all uplink ports down, needs overlay escape
第三方 DHCP服务器地址
Radius服务器地址
SSO服务器地址

## 03 Overlay Planning
| VRF name | Description | VXLAN ID range | L3VNI
| VPN-XXXX | for clients | 10001-19999 | 10000
| vpn-default | inbound management | 4093-4094 | 4092
|  | Data Vlan |  |  |  | Voice Vlan
Floor | Description | IP Subnet | Gateway | VLAN ID(Old) | VXLAN ID | IP block | Gateway | VLAN ID(Old) | VXLAN ID
every floor
Garden Floor
Ground Floor
2nd Floor
3rd Floor
4th Floor

## 03-License Information
一期
BOM | 描述 |  | 数量
3132A09X | LIS-UIS-CAS-2CPU-A | 灵活License授权函-H3C UIS-UISCM1CASSTD-UIS计算虚拟化软件(UIS CAS) License费用-管理2个物理CPU-国内版 | 9
3132A08D | LIS-UIS-MGR-STD-E-2CPU-A | 灵活License授权函-H3C UIS-UISBM1STDEA-UIS超融合管理软件(UIS Manager)增强包License费用-管理2个物理CPU-国内版 | 9
3132A06U | LIS-UIS-ONEStor-BLOCK-ENT-2CPU | 灵活License授权函-H3C ONEStor-ST0M2LOSBLOCKENT-UIS存储虚拟化软件(UIS ONEStor)-块存储企业版License费用-管理2个物理CPU-国内版 | 9
3132A04R | LIS-UIS-MANGERA-STD-2 | 灵活License授权函-H3C UIS-UIS7M1MAGA-UIS超融合管理软件(UIS Manager)标准版License费用-管理2个物理CPU-国内版 | 9
3130A426 | LIS-IMC9-NSM | License授权函-H3C U-Center2.0-SWCM1NSM-NSM网络设备管理授权函-国内海外合一版 | 1
3130A423 | LIS-IMC9-NSMA-25 | License授权函-H3C U-Center2.0-SWCM1NSMA-NSM网络设备管理-25 License-国内海外合一版 | 1
3130A3RN | LIS-UCENTER2-IOP | License授权函-H3C U-Center2.0-SWBM1IOPD-智能运维软件-国内海外合一版 | 1
3130A3RH | LIS-UCENTER2-IOM-25 | License授权函-H3C U-Center2.0-SWBM1IOPDB-IOM-25 License-国内海外合一版 | 1
3130A3RE | LIS-UCENTER2-IOM | License授权函-H3C U-Center2.0-SWBM1IOPDA-IOM基础设施运维授权函-国内海外合一版 | 1
Campus license 还没发货

## 04 Customer Requirements Change
No | Piority | Status | Description | Next Step & Solution | Open Date | Close Date | Owner
1 | Normal
2 | Normal
3 | Low
4 | High
5 | High
6 | High
NOTE：for new requirements that affect the initial plan of the project，need to talk to PM for future discussion

## 04 Password
Items | IP/URL | Account | Password | Methods
leaf |  | admin |  | SSH
access |  | admin |  | SSH
HDM |  | admin |  | HTTPS
Server background |  | root |  | SSH
AD-Campus |  | admin |  | HTTPS